## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Project Initiation & Planning (finalise objectives, scope and team roles) | 1 | 1 | 1 |  | 25%
Research & Evidence Collection | 2 | 7 |  |  | 100%
Red Team simulation | 9 | 7 |  |  | 35%
Blue Team Monitoring & Incident Response Evaluation | 16 | 14 |  |  | 10%
Analysis & Recommendations Finalised | 30 | 13 |  |  | 85%
Final Project Report Submission | 43 | 3 |  |  | 85%
Activity 07
Activity 08
Activity 09
Activity 10
Activity 11
Activity 12
Activity 13
Activity 14
Activity 15
Activity 16
Activity 17
Activity 18
Activity 19
Activity 20
Activity 21
Activity 22
Activity 23
Activity 24
Activity 25
Activity 26